## Sheet1
Task | Start Date | Expected Completion Date | isCompleted | Effort (hrs.)
Deliverable 1 – Requirements Document and Prototype
Functional and non-functional system requirements | 02/10/2016 | 02/12/2016 | yes | n/a
Domain Model | 02/13/2016 | 02/15/2016 | yes | n/a
Use Cases | 02/16/2016 | 02/20/2016 | yes | n/a
Requirements-level sequence diagram for “Add Album” use case | 02/16/2016 | 02/20/2016 | yes | n/a
Source code of prototype implementation of “Add Album” use case on each supported platform | 02/16/2016 | 02/20/2016 | yes | n/a
Implementation-level sequence diagram for “Add Album” use case for each supported platform | 02/16/2016 | 02/20/2016 | yes | n/a
Work plan for remaining iterations | 02/20/2016 | 02/21/2016 | yes | n/a
Make sure everything is in order for submission of deliverable | 02/21/2016 | 02/22/2016 | yes | n/a
Deliverable 2 – Design Specification
Description of architecture of proposed solution including block diagram | 02/26/2016 | 02/29/2016 | yes | 3
Description of detailed design of proposed solution including class diagram | 02/26/2016 | 02/29/2016 | yes | 2.5
Implement Requirement "HAS7706" | 02/27/2016 | 03/06/2016 | yes | 2*
Implement Requirement "HAS7707" | 02/27/2016 | 03/06/2016 | yes | 1.5*
Implement Requirement "HAS7708" | 02/27/2016 | 03/06/2016 | yes | 2*
Update of work plan | 03/05/2016 | 03/06/2016 | yes | 0.5
Make sure everything is in order for submission of deliverable | 03/06/2016 | 03/07/2016 | yes | 0.25
Deliverable 3 – Quality Assurance Plan
Description of Unit Test Plan | 03/08/2016 | 03/17/2016 | no | 3
Description of Integration Test Plan | 03/08/2016 | 03/17/2016 | no | 2
Description of System Test Plan | 03/08/2016 | 03/17/2016 | no | 2
Implement Requirement "HAS7702" | 03/22/2016 | 03/25/2016 | no | 1*
Implement Requirement "HAS7703" | 03/10/2016 | 03/18/2016 | no | 1*
Implement Requirement "HAS7704" | 03/10/2016 | 03/18/2016 | no | 2*
Implement Requirement "HAS7705" | 03/10/2016 | 03/18/2016 | no | 0.5*
Implement Requirement "HAS7709" | 03/10/2016 | 03/18/2016 | no | 1*
Implement Requirement "HAS7711" | 03/10/2016 | 03/18/2016 | no | 2*
Update of work plan | 03/19/2016 | 03/20/2016 | no | 0.5
Make sure everything is in order for submission of deliverable | 03/20/2016 | 03/21/2016 | no | 0.25
Deliverable 4 – Release Pipeline Plan
Description of release pipeline | 03/22/2016 | 03/25/2016 | no | 2.5
Implement Requirement "HAS7710" | 03/22/2016 | 03/25/2016 | no | 1.5*
Implement Requirement "HAS7712" | 03/22/2016 | 03/25/2016 | no | 1.5*
Implement Requirement "HAS7713" | 03/22/2016 | 03/25/2016 | no | 2*
Implement Requirement "HAS7714" | 03/22/2016 | 03/25/2016 | no | 1.5*
Implement Requirement "HAS7715" | 03/22/2016 | 03/25/2016 | no | 1*
Update of work plan | 03/26/2016 | 03/27/2016 | no | 0.5
Make sure everything is in order for submission of deliverable | 03/27/2016 | 03/27/2016 | no | 0.3
Deliverable 5 – Presentation
Prepare Powerpoint presentation | 03/28/2016 | 04/09/2016 | no | 4
Prepare script to say | 03/28/2016 | 04/09/2016 | no | 3
Fully test application | 03/28/2016 | 04/13/2016 | no | 4*
Present project | 04/14/2016 | 04/14/2016 | no | 0.4
Deliverable 6 – Final Application
Source code of full implementation on each supported platform | 04/15/2016 | 04/15/2016 | no | 5*
* Hours are calculated based on an average amount of time worked on the iteration by EACH of the three (3) software developpers for the web, mobile and desktop applications