## Sheet1
Task | Start Date | Expected Completion Date | isCompleted
Deliverable 1 – Requirements Document and Prototype
Functional and non-functional system requirements | 02/10/2016 | 02/12/2016 | yes
Domain Model | 02/13/2016 | 02/15/2016 | yes
Use Cases | 02/16/2016 | 02/20/2016 | yes
Requirements-level sequence diagram for “Add Album” use case | 02/16/2016 | 02/20/2016 | yes
Source code of prototype implementation of “Add Album” use case on each supported platform | 02/16/2016 | 02/20/2016 | yes
Implementation-level sequence diagram for “Add Album” use case for each supported platform | 02/16/2016 | 02/20/2016 | yes
Work plan for remaining iterations | 02/20/2016 | 02/21/2016 | yes
Make sure everything is in order for submission of deliverable | 02/21/2016 | 02/22/2016 | yes
Deliverable 2 – Design Specification
Description of architecture of proposed solution including block diagram | 02/26/2016 | 02/29/2016 | no
Description of detailed design of proposed solution including class diagram | 02/26/2016 | 02/29/2016 | no
Implement Requirement "HAS7702" | 02/27/2016 | 03/06/2016 | no
Implement Requirement "HAS7703" | 02/27/2016 | 03/06/2016 | no
Implement Requirement "HAS7704" | 02/27/2016 | 03/06/2016 | no
Implement Requirement "HAS7705" | 02/27/2016 | 03/06/2016 | no
Update of work plan | 03/05/2016 | 03/06/2016 | no
Make sure everything is in order for submission of deliverable | 03/06/2016 | 03/07/2016 | no
Deliverable 3 – Quality Assurance Plan
Description of unit testing | 03/08/2016 | 03/17/2016 | no
Description of component testing | 03/08/2016 | 03/17/2016 | no
Description of system testing | 03/08/2016 | 03/17/2016 | no
Description of performance/stress testing | 03/08/2016 | 03/17/2016 | no
Implement Requirement "HAS7708" | 03/10/2016 | 03/18/2016 | no
Implement Requirement "HAS7709" | 03/10/2016 | 03/18/2016 | no
Implement Requirement "HAS7710" | 03/10/2016 | 03/18/2016 | no
Implement Requirement "HAS7711" | 03/10/2016 | 03/18/2016 | no
Update of work plan | 03/19/2016 | 03/20/2016 | no
Make sure everything is in order for submission of deliverable | 03/20/2016 | 03/21/2016 | no
Deliverable 4 – Release Pipeline Plan
Description of release pipeline | 03/22/2016 | 03/25/2016 | no
Implement Requirement "HAS7712" | 03/22/2016 | 03/25/2016 | no
Implement Requirement "HAS7713" | 03/22/2016 | 03/25/2016 | no
Implement Requirement "HAS7714" | 03/22/2016 | 03/25/2016 | no
Update of work plan | 03/26/2016 | 03/27/2016 | no
Make sure everything is in order for submission of deliverable | 03/27/2016 | 03/27/2016 | no
Deliverable 5 – Presentation
Prepare Powerpoint presentation | 03/28/2016 | 04/09/2016 | no
Prepare script to say | 03/28/2016 | 04/09/2016 | no
Fully test application | 03/28/2016 | 04/13/2016
Present project | 04/14/2016 | 04/14/2016 | no
Deliverable 6 – Final Application
Source code of full implementation on each supported platform | 04/15/2016 | 04/15/2016 | no